## Blad1
Category |  | 2021-08-30 | 2021-09-06 | 2021-09-13 | 2021-09-20 | 2021-09-27 | 2021-10-04 | 2021-10-11 | 2021-10-18 | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-01-03 | 2021-01-10
| To Do | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Bootcamp | One Slide Idea | bar: Week 1
Reflectie Leeruitkomsten | bar: Week 2
Planning | bar: Week 1
Kennismaken Web-dev | bar: Week 1 to Week 2
Analyse | Inleiding | bar: Week 2
Projectomschrijving | bar: Week 2
Requirements | bar: Week 2
UI Design | bar: Week 2 to Week 3
Definition of Done | bar: Week 2
Prototype | bar: Week 2 to Week 3
Use Cases | bar: Week 2 to Week 3
Test Cases | bar: Week 3 to Week 4
Tests | bar: Week 4 to Week 6
Ontwerp | Architectuur | bar: Week 4 to Week 12
UML | bar: Week 4 to Week 12
Database design | bar: Week 4 to Week 11
Bouw | Database maken | bar: Week 4
Tables maken | bar: Week 4 to Week 12
Project (MVC) opzetten | bar: Week 2 to Week 5
Interfaces toevoegen | bar: Week 6 to Week 9
Datalaag toevoegen | bar: Week 5 to Week 13
Algorimtiek | Pathfinding opdracht | bar: Week 8 to Week 11
Containerschip opdracht | bar: Week 13 to Week 16
A | Afgerond
X | Aan gewerkt